## Risk Overview
風險總覽 Risk Overview — 2025年10月
- 本月新增風險事件 9 件，已結案 5 件。
- 最高風險：產能不足（影響 Widget-B）
- 供應商風險指數：38%（正常）
- 本月 P90 延遲天數：4 天

## 異常記錄 Exception Log
Exception ID | Date | Category | Product | Supplier | Description | Severity | Status | Resolution
EXC-202510-001 | 2025/10/09 | Demand Spike | Cap-220uF | TSMC | 交期延遲超過 SLA | High | Open | 供應商扣款
EXC-202510-002 | 2025/10/27 | Quality Defect | Sensor-X | ASE Group | 進料品質不合格 | Critical | Open | 已退貨換新
EXC-202510-003 | 2025/10/17 | Quality Defect | Widget-A | TDK | 文件不齊全 | Medium | Open | 供應商扣款
EXC-202510-004 | 2025/10/10 | Quality Defect | Module-M1 | Murata | 包裝破損 | Low | Resolved | 補貨中
EXC-202510-005 | 2025/10/23 | Material Shortage | Widget-A | ASE Group | 進料品質不合格 | High | Investigating | 補貨中
EXC-202510-006 | 2025/10/14 | Logistics Delay | Widget-B | Delta Electronics | 報關延誤 | Medium | Resolved | 持續追蹤
EXC-202510-007 | 2025/10/27 | Quality Defect | Relay-K1 | Murata | 數量短缺 | Medium | Investigating | 已關閉
EXC-202510-008 | 2025/10/28 | Quality Defect | Widget-A | Foxconn | 包裝破損 | High | Closed | 補貨中
EXC-202510-009 | 2025/10/07 | Material Shortage | Cap-220uF | Samsung SDI | 進料品質不合格 | Low | Resolved | 已關閉
EXC-202510-010 | 2025/10/03 | System Error | Board-PCB3 | Yageo | 文件不齊全 | Low | Resolved | 已退貨換新
EXC-202510-011 | 2025/10/05 | Material Shortage | Module-M1 | TSMC | 報關延誤 | Medium | Closed | 供應商扣款
EXC-202510-012 | 2025/10/13 | Quality Defect | Sensor-X | Murata | 文件不齊全 | Low | Investigating | 持續追蹤
EXC-202510-013 | 2025/10/16 | Capacity Constraint | Relay-K1 | Samsung SDI | 數量短缺 | Critical | Investigating | 供應商扣款
EXC-202510-014 | 2025/10/22 | Logistics Delay | Cap-220uF | Yageo | 報關延誤 | Low | Closed | 持續追蹤
EXC-202510-015 | 2025/10/16 | System Error | Sensor-X | Yageo | 包裝破損 | Medium | Open | 已退貨換新

## Risk Matrix
風險矩陣 Risk Heat Map
Risk Category | Likelihood | Impact | Score | Mitigation
供應中斷 | 3 | 4 | 12 | 合約條款
品質異常 | 5 | 3 | 15 | 即時監控
交期延遲 | 3 | 5 | 15 | 即時監控
價格波動 | 5 | 3 | 15 | 合約條款
產能不足 | 3 | 1 | 3 | 備援供應商
庫存過高 | 4 | 3 | 12 | 合約條款
匯率風險 | 1 | 4 | 4 | 合約條款